## Online Gantt 20240320
Outline Level | ID | Name | Start | Finish | Duration | % Complete | Predecessors | Resource Names | Color | Notes
1 | 1 | Planning | 2024-03-18 | 2024-04-05 | 15 day | 50 |  |  |  | <p><br></p>
2 | 2 | Determine project requirements | 2024-03-18 | 2024-03-22 | 5 day | 80 |  | Team Member 1 | 121 | <p><br></p>
2 | 3 | Secure project sponsorship | 2024-03-25 | 2024-03-29 | 5 day | 50 | 2FS | Team Member 2 | 211 | <p><br></p>
2 | 4 | Secure core resources | 2024-04-01 | 2024-04-05 | 5 day | 20 | 3FS | Team Member 3 | 301 | <p><br></p>
1 | 5 | Analysis/Software Requirements | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 6 | Conduct needs analysis | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 7 | Draft preliminary software specifications | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 8 | Develop preliminary budget | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 9 | Team review on software specifications budget | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 10 | Incorporate feedback on software specifications | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 11 | Develop delivery timeline | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 12 | Obtain approvals to proceed | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
1 | 13 | Design | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 14 | Develop functional specifications | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 15 | Design Use case Diagram | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 16 | Design Prototype(UI/UX) | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 17 | Design Class Diagram | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 18 | Review functional specifications | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 19 | Incorporate feedback | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 20 | Obtain approval to proceed | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
1 | 21 | Implementation/Development | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 22 | Identify design parameters | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 23 | Assign development staff | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 24 | Code development | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 25 | Code review/testing (Developer) | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
1 | 26 | Testing | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 27 | Develop unit test plans | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 28 | Develop integration test plans | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 29 | Unit Testing | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 30 | Review modular code | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 31 | Test component modules | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 32 | Identify anomalies | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 33 | Modify code | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 34 | Re-test modified code | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 35 | Integration Testing | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 36 | Test module integration | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 37 | Identify anomalies | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 38 | Modify integrated code | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
3 | 39 | Re-test integrated code | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
1 | 40 | Documentation | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 41 | Develop Support specifications | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 42 | Develop Support system | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 43 | Review Support documentation | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 44 | Incorporate feedback on support documentation | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 45 | Develop User manual specifications | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 46 | Develop User manual | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 47 | Review all documentation | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 48 | Incorporate feedback on Documentations | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
1 | 49 | Deployment | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 50 | Determine final deployment strategy | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 51 | Develop deployment methodology | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 52 | Design deployment diagram | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 53 | Secure deployment recources | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>
2 | 54 | Deploy Software | 2024-03-18 | 2024-03-18 | 1 day | 0 |  |  |  | <p><br></p>