## Sheet1
Game Distribution Platform (Game Arcade)
Project Risk, Impact, Risk level
Date of last review: 30/04/2024
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
GDPR0 | Planning
GDPR0.1 | Secure project sponsorship | Lack of Stakeholder Alignment | Clear understanding and communication between both parties | medium | Project manager
GDPR0.2 | Secure core resources | Resource constraints | Resource Planning, Collaboration with Operations | low | Project manager
GDPR1 | Analysis/Software Requirements
GDPR1.1 | Draft preliminary software specifications | Unclear Requirements Gathering | Iterative Approach | low | Project analyst
GDPR1.2 | Develop preliminary budget | Inaccurate Cost Estimation | Contingency Planning, Detailed Cost Breakdown: | low | Project analyst
GDPR1.3 | Obtain approvals to proceed (concept, timeline, budget) | Lack of Stakeholder Buy-In | Address Concerns, Clear Presentation | medium | Project analyst
GDPR2 | Design
GDPR2.1 | Develop functional specifications | Ambiguity in Requirements | Documentation Precision, Stakeholder Collaboration | low | UI/UX designer
GDPR2.2 | Develop prototype based on functional specifications | Misinterpretation of Specifications | Iterative Prototyping, Clear Communication | high | UI/UX designer
GDPR2.3 | Review functional specifications | Lack of Thoroughness in Review | Diverse Reviewers, Structured Review Process | low | UI/UX designer
GDPR2.4 | Obtain approval to proceed | Uncertainty or Resistance from Decision-Makers | Compelling Presentation, Address Concerns | low | UI/UX designer
GDPR4 | Development
GDPR4.1 | Identify design parameters | Unclear or Evolving Design Requirements | Continuous Requirement Refinement, Documentation Updates | medium | Developer
GDPR4.2 | Assign development staff | Skills and Resource Allocation | Skill Assessment, Training and Collaboration | high | Developer
GDPR4.3 | Develop code | Code Quality and Consistency | Coding Standards, Code Reviews | low | Developer
GDPR4.4 | Developer testing (primary debugging) | Inadequate Testing Coverage | Comprehensive Test Plans, Automated Testing | low | Developer
GDPR5 | Testing
GDPR5.1 | Develop unit test plans using product specifications | Incomplete or Inaccurate Specifications | Specification Review, Traceability Matrix | high | Quality Tester
GDPR5.2 | Develop integration test plans using product specifications | Complex Interactions and Dependencies | Incremental Testing Approach, Mocking and Simulation | high | Quality Tester
GDPR6 | Unit Testing
GDPR6.1 | Test component modules to product specifications | Inadequate Test Coverage | Test Case Prioritization, Equivalence Partitioning | high | Quality Tester
GDPR6.2 | Identify anomalies to product specifications | Ambiguities or Conflicting Specifications | Traceability and Documentation | high | Quality Tester
GDPR6.3 | Modify code | Addressing Identified Anomalies | Regression Testing, Code Reviews and Collaboration | high | Quality Tester
GDPR7 | Integration Testing
GDPR7.1 | Test module integration | Complex Integration Scenarios | Incremental Integration, Stubbing and Mocking | high | Quality Tester
GDPR7.2 | Identify anomalies to specifications | Integration Inconsistencies | Cross-Module Validation, Logging and Tracing | high | Quality Tester
GDPR7.3 | Modify code | Addressing Integration Anomalies | Collaborative Debugging, Version Control and Rollbacks | high | Quality Tester
GDPR7.4 | Re-test modified code | Regression and Integration Testing Overheads | Automated Regression Testing, Comprehensive Test Suites | low | Quality Tester
GDPR8 | Documentation
GDPR8.1 | Develop Help specification | Unclear or Incomplete Requirements | Stakeholder Involvement, Prototype and Feedback | low | Technical writer
GDPR8.2 | Develop Help system | Complex Information Structure | Information Architecture, Usability Testing | medium | Technical writer
GDPR8.3 | Develop user manuals specifications | Balancing Technical Details and User Comprehension | User-Centric Approach, Visual Aids | low | Technical writer
GDPR8.4 | Develop user manuals | Consistency and Clarity | Style Guides and Templates, Peer Review | medium | Technical writer
GDPR8.5 | Incorporate user documentation feedback | Diverse User Feedback | Feedback Analysis, Prioritization | low | Technical writer
GDPR9 | Deployment
GDPR9.1 | Develop deployment methodology | Complex Deployment Scenarios | Standardization, Testing Environments | low | Deployment Team
GDPR9.2 | Secure deployment resources | Resource Availability and Allocation | Resource Planning, Collaboration with Operations | high | Deployment Team
GDPR9.3 | Train support staff | Knowledge Transfer and Training Efficiency | Comprehensive Training Materials, Hands-on Exercises | high | Deployment Team
GDPR10 | Post Implementation Review
GDPR10.1 | Distribute to team members | Communication and Distribution Efficiency | Centralized Repository, Regular Updates | medium | SQA engineer
GDPR10.2 | Create software maintenance team | Team Composition and Skills | Skill Assessment, Continuous Training | high | SQA engineer
GDPR8.13